## Sprint Backlog
Sr. | US ID | Role | User Story | MoSCoW | Risk (Impl.) | Dependency | Story Points | Priority | Acceptance Criteria
1 | US-01 | Borrower | As a borrower, I want to register an account so that I can create a secure account. | Must | Medium | - | 5 | Highest | - User can register using mobile number or email - System sends an OTP to verify the entered mobile number or email - User must enter the correct OTP within the valid time to continue - System shows an error if the OTP is incorrect or expired - System blocks registration if the mobile number or email is already in use - User's password must meet the minimum security requirements - Account is created only after successful OTP verification
2 | US-02 | Borrower | As a borrower, I want to reset my password so that I can regain access to my account. | Must | Low | US-01 | 2 | High | - User can request a password reset from the login screen - System sends an OTP to the registered mobile number or email - User must enter the correct OTP to proceed with the reset - System shows an error if the OTP is incorrect or expired - User can set a new password that meets the minimum security requirements - User is logged out of all other active sessions after a successful reset
3 | US-03 | Borrower | As a borrower, I want to complete my KYC so that my identity can be verified. | Must | High | US-01 | 13 | Highest | - User can complete KYC by entering Aadhaar number, PAN number, and uploading required documents - User must upload address proof and income proof as part of KYC - User must complete a liveness selfie check as part of KYC - System shows an error if any required KYC field or document is missing - KYC is marked as submitted only once all required details and documents are provided - Uploaded documents are securely stored and only accessible to the user and authorised staff
4 | US-04 | Borrower | As a borrower, I want to track the status of my KYC submission so that I know whether my documents have been verified, are pending review, or have been rejected. | Must | Low | US-03 | 2 | High | - User can view their current KYC status at any time - KYC status clearly shows whether it is Not Started, In Progress, Submitted, Verified, or Rejected - Status updates automatically when an officer reviews the KYC documents - User does not need to refresh or relaunch the app to see the latest status - If rejected, user can see which specific document caused the rejection
5 | US-05 | Borrower | As a borrower, I want to resubmit specific KYC documents that were rejected so that I can correct my submission and continue the verification process. | Must | Medium | US-03, US-27 | 5 | High | - User can view which specific KYC documents were rejected - User can re-upload only the rejected documents, not the entire KYC - System replaces the old rejected document with the newly uploaded one - Resubmitted documents are sent back to the officer for review - KYC status updates automatically once all rejected documents are resubmitted
6 | US-06 | Borrower | As a borrower, I want to use the EMI calculator to estimate my monthly payment for any loan amount, tenure, and interest rate so that I can make an informed decision before applying. | Must | Low | - | 3 | Highest | - User can access the EMI calculator without logging in - User can enter any loan amount, tenure, and interest rate - System calculates and displays the EMI based on the entered values - System shows the total interest payable and total repayment amount - EMI updates instantly whenever the user changes any input value
7 | US-07 | Borrower | As a borrower, I want to apply for a new loan so that I can initiate a loan request. | Must | High | US-03, US-06, US-65 | 13 | Highest | - User can select a loan type before starting the application - User can enter the desired loan amount and tenure within the allowed limits - User can preview the EMI before submitting the application - User must upload all required documents based on the selected loan type - System blocks submission if KYC is not completed - System blocks submission if any required document is missing - A unique application number is generated once the application is submitted - User cannot edit the loan amount or tenure after submission
8 | US-08 | Borrower | As a borrower, I want to track my loan application status in real time so that I always know where my application stands. | Must | Medium | US-07 | 8 | High | - User can view the current status of their loan application at any time - Status clearly shows the stage — Submitted, Under Review, Approved, Disbursed, or Rejected - Status updates automatically without the user needing to refresh the app - User can tap on a past stage to see when it was reached
9 | US-09 | Borrower | As a borrower, I want to upload additional documents so that I can provide missing information and allow my application to continue processing. | Must | Low | US-27 | 3 | High | - User can upload additional documents only when requested by the loan officer - System only accepts supported file formats (e.g. PDF, JPG, PNG) - System shows an error if the file size exceeds the allowed limit - Officer is notified once the requested document is uploaded - Application moves forward once all requested documents are submitted
10 | US-10 | Borrower | As a borrower, I want to view the reason my loan application was rejected so that I understand the decision and know what to address before reapplying. | Must | Low | US-46, US-32 | 2 | High | - User can view the reason their loan application was rejected - Rejection reason is shown exactly as entered by the officer or manager - This screen is only visible if the application status is Rejected - User can start a new loan application directly from this screen
11 | US-11 | Borrower | As a borrower, I want to review and respond to remarks when my application is sent back for revision so that I can address the officer's concerns. | Must | Medium | US-47 | 3 | Medium | - User can view the manager's remarks when an application is sent back for revision - User can respond to the remarks and/or re-upload the relevant documents - User can resubmit the application after addressing the remarks - Application moves back to the loan officer's queue after resubmission
12 | US-12 | Borrower | As a borrower, I want to view my active loan details so that I have full visibility into my current loan. | Must | Low | US-55 | 5 | High | - User can view their active loan details including disbursement date and amount - User can view the outstanding principal and interest amount - User can view the current interest rate applied to the loan - All loan details shown are read-only and cannot be edited by the user
13 | US-13 | Borrower | As a borrower, I want to view my full EMI details so that I can plan my repayments effectively. | Must | Low | US-55 | 3 | High | - User can view the complete EMI schedule for their loan - Each EMI entry shows the due date, amount, and principal/interest breakdown - Each EMI is clearly marked as Paid, Upcoming, or Overdue - Overdue EMIs show any applicable penalty amount
14 | US-14 | Borrower | As a borrower, I want to pay my EMI so that I can settle my repayments securely. | Must | High | US-13 | 8 | Highest | - User can pay an EMI directly through the app - User can choose to pay via UPI, card, or netbanking - System shows the exact EMI amount, including any penalty, before payment - User receives a confirmation once the payment is successfully completed - System shows a clear status if the payment is still being processed - EMI status updates to Paid automatically after a successful payment - Loan status updates to Closed if this was the final EMI
15 | US-15 | Borrower | As a borrower, I want to view my complete payment history so that I can track every repayment. | Must | Low | US-14 | 3 | High | - User can view their complete payment history - Each entry shows the date, amount, payment mode, and reference number - Cash payments and online payments are both shown in the same list - User can scroll through past payments without performance issues
16 | US-16 | Borrower | As a borrower, I want to download my sanction letter and loan agreement so that I have official documentation of my loan approval and terms. | Must | Medium | US-34 | 3 | High | - User can download the sanction letter once the loan is approved - User can download the loan agreement once the loan is disbursed - Both documents are downloaded as PDF files - System shows an error if the document is not yet available
17 | US-17 | Borrower | As a borrower, I want to send and receive in-app messages with my assigned loan officer about my application so that all communication is documented in one place. | Should | Low | US-36 | 3 | Medium | - User can send and receive messages with their assigned loan officer - Messages are linked to the specific loan application - User receives a notification when the officer replies - User can view the full message history for that application at any time
18 | US-18 | Borrower | As a borrower, I want to receive push notifications for all key loan events so that I never miss a critical update about my loan. | Must | Medium | US-08 | 5 | High | - User receives push notifications for key events such as OTP, KYC status, application updates, and EMI reminders - User receives a notification when an EMI is due soon and when an EMI is overdue - User receives a notification when a payment is confirmed - Tapping a notification takes the user directly to the relevant screen - All notifications are also available to view inside the app's notification list
19 | US-19 | Borrower | As a borrower, I want to view and update my profile information so that my account details remain accurate. | Should | Low | US-01 | 2 | Low | - User can update their name, phone number, and address - System sends an OTP to verify any change to the phone number - Updated information is saved immediately after confirmation - System shows an error if the update fails
20 | US-20 | Borrower | As a borrower, I want to view a repayment dashboard showing my upcoming EMI due date, total outstanding balance, overdue amount if any, and a quick Pay button so that I can see my repayment health at a glance and act immediately. | Must | High | US-14, US-13 | 8 | High | - User can view their next EMI due date and total outstanding balance in one place - User can view the overdue amount, if any, on the same screen - A Pay button is shown when an EMI is due or overdue - Tapping Pay takes the user directly into the payment flow for that EMI
21 | US-21 | Borrower | As a borrower, I want to view my credit score and the bureau it was sourced from so that I can understand my creditworthiness. | Should | Medium | US-19 | 3 | Low | - User can view their current credit score - User can view which credit bureau the score was sourced from - System shows a clear message if no credit score is available yet - Credit score is shown as read-only and cannot be edited by the user
22 | US-22 | Loan Officer | As a loan officer, I want to log in to the app so that I can access my assigned loan processing functions. | Must | Medium | - | 3 | Highest | - Officer can log in using their employee credentials - System grants access only to the features and data permitted for the loan officer role - System shows an error for incorrect login credentials - Officer is logged out automatically after a defined period of inactivity
23 | US-23 | Loan Officer | As a loan officer, I want to see all my assigned loan applications in a dashboard so that I can identify which ones need action. | Must | Medium | US-07 | 5 | High | - Officer can view all loan applications assigned to them in one dashboard - Applications needing action are clearly highlighted - Officer can see the applicant name, loan type, amount, and status at a glance - Dashboard updates automatically when a new application is assigned
24 | US-24 | Loan Officer | As a loan officer, I want to view the full detail of a loan application so that I can assess all borrower information. | Must | Medium | US-23 | 5 | High | - Officer can open any assigned application to view its full details - Officer can view the applicant's information, requested amount, and purpose - Officer can view and open all documents uploaded for the application - All borrower-submitted information is shown as read-only
25 | US-25 | Loan Officer | As a loan officer, I want to view a borrower's credit score and risk summary so that I can evaluate their creditworthiness before making a recommendation. | Must | High | US-24 | 5 | High | - Officer can view the borrower's credit score on the application detail screen - Officer can view a summary of the borrower's credit risk - System shows a clear message if the credit score is not yet available - Officer can only view this information for applications assigned to them
26 | US-26 | Loan Officer | As a loan officer, I want to request additional documents from a borrower so that I can obtain missing information needed to process the application. | Must | Low | US-23 | 3 | High | - Officer can request additional documents from the borrower - Officer can specify which document(s) are needed - Officer can add a note explaining the request - Borrower is notified immediately when a document is requested - Application is marked as awaiting borrower response until the document is provided
27 | US-27 | Loan Officer | As a loan officer, I want to review documents resubmitted by a borrower so that I can continue processing the application. | Must | Low | US-26, US-05 | 3 | High | - Officer can view documents resubmitted by the borrower - Officer can mark each document as verified or rejected - Officer can add a remark if a document is rejected again - Application moves forward once all requested documents are verified
28 | US-28 | Loan Officer | As a loan officer, I want to reject an ineligible loan application with a mandatory reason so that the borrower is informed and the decision is permanently recorded. | Must | Low | US-24 | 3 | High | - Officer can reject an ineligible loan application - System requires a reason before the rejection can be confirmed - Borrower is notified of the rejection and the reason - Rejected application is recorded permanently and cannot be edited
29 | US-29 | Loan Officer | As a loan officer, I want to recommend an eligible loan application to the manager so that it proceeds for final approval. | Must | Low | US-24 | 3 | High | - Officer can recommend an eligible application to the manager - Recommend option is only available once the officer's review is complete - Application appears in the manager's queue immediately after recommendation - Officer cannot recommend the same application more than once
30 | US-30 | Loan Officer | As a loan officer, I want to receive and review manager send-back remarks so that I can address the gaps and resubmit the application for approval. | Must | Low | US-47 | 3 | High | - Officer can view the manager's remarks when an application is sent back - Officer can take the necessary action to address the remarks - Officer can resubmit the application to the manager after addressing the gaps - Officer is notified as soon as an application is sent back
31 | US-31 | Loan Officer | As a loan officer, I want to view the manager's decision on a recommended application so that I can take the appropriate next action. | Must | Low | US-43, US-44 | 2 | High | - Officer can view the manager's final decision on a recommended application - Decision clearly shows whether it was Approved, Rejected, or Sent Back - Officer is notified as soon as the manager makes a decision - Officer can take the next appropriate action directly from this screen
32 | US-32 | Loan Officer | As a loan officer, I want to generate and share the loan sanction letter for a manager-approved application so that the borrower receives their official approval document. | Must | High | US-43 | 8 | High | - Officer can generate the sanction letter once the manager approves the application - Sanction letter includes the approved loan terms - Officer can share the sanction letter directly from the app - Borrower can independently access the same sanction letter from their account
33 | US-33 | Loan Officer | As a loan officer, I want to send and receive in-app messages with a borrower about their application so that all communication is documented in one place. | Should | Low | US-24, US-01 | 5 | Medium | - Officer can send and receive messages with the borrower about their application - Messages are linked to the specific loan application - Officer receives a notification when the borrower sends a new message - Officer can view the full message history for that application
34 | US-34 | Loan Officer | As a loan officer, I want to send a message to the manager about a specific loan application so that I can seek clarification on decisions or approvals. | Should | Low | US-36 | 3 | Low | - Officer can send a message to the manager about a specific application - Manager is notified when a new message is received - Message is linked to the relevant loan application - Officer can view the full message history with the manager
35 | US-35 | Loan Officer | As a loan officer, I want to view my assigned portfolio of active loans so that I can monitor the post-disbursement status of borrowers I processed. | Must | Medium | US-55 | 5 | Medium | - Officer can view a list of all active loans they have processed - Officer can see the current status of each loan at a glance - Officer can see the outstanding balance for each loan - List only includes loans the officer personally processed
36 | US-36 | Loan Officer | As a loan officer, I want to track the repayment status of my assigned borrowers so that I can identify who is on track and who is falling behind. | Must | Medium | US-37 | 5 | Medium | - Officer can view the repayment status of each assigned borrower - System clearly shows which borrowers are on track and which are falling behind - Officer can sort or filter the list to identify at-risk borrowers quickly - Status reflects the latest repayment data available
37 | US-37 | Loan Officer | As a loan officer, I want to flag overdue borrower accounts so that they are escalated for NPA monitoring before the threshold is reached. | Must | High | US-38 | 5 | Medium | - Officer can flag an overdue borrower account for early NPA monitoring - Officer must provide a reason when flagging an account - Flagged accounts are visible to both the officer and their manager - Flagging does not change the loan's status by itself
38 | US-38 | Loan Officer | As a loan officer, I want to receive push notifications for all key events on my assigned applications so that I can act promptly without constantly checking the app. | Should | Medium | US-23 | 5 | Medium | - Officer receives push notifications for key events on their assigned applications - Notifications include new submissions, document resubmissions, and borrower messages - Officer receives an alert when an assigned loan becomes overdue or reaches NPA - Tapping a notification takes the officer directly to the relevant application
39 | US-39 | Manager | As a manager, I want to log in to the app so that I can access data my role permits. | Must | Medium | - | 3 | Highest | - Manager can log in using their employee credentials - System grants access only to the features and data permitted for the manager role - System shows an error for incorrect login credentials - Manager is logged out automatically after a defined period of inactivity
40 | US-40 | Manager | As a manager, I want to see all officer-recommended loan applications in a prioritised list so that I can work through them. | Must | Medium | US-29 | 5 | High | - Manager can view all officer-recommended applications in one prioritised list - List clearly shows the applicant, amount, and recommending officer - Oldest unactioned applications are surfaced first - List updates automatically as new recommendations come in
41 | US-41 | Manager | As a manager, I want to approve a loan application and set the disbursement terms so that the borrower's loan can proceed. | Must | High | US-40 | 8 | High | - Manager can approve a loan application after reviewing its full details - Manager can set or adjust the final disbursement amount, tenure, and interest rate - System requires all terms to be confirmed before approval is finalised - Application moves to the approved list once confirmed
42 | US-42 | Manager | As a manager, I want to reject a loan application with a required reason so that the borrower understands the decision and the rejection is auditable. | Must | Low | US-40 | 3 | High | - Manager can reject a loan application - System requires a reason before the rejection can be confirmed - Borrower is notified of the rejection and the reason - Rejected application is recorded permanently
43 | US-43 | Manager | As a manager, I want to return an application to the officer with specific remarks so that they can address gaps before I make a final decision. | Must | Low | US-40 | 3 | High | - Manager can return an application to the officer for revision - System requires specific remarks before the application can be sent back - Officer is notified immediately when an application is sent back - Application returns to the officer's active queue
44 | US-44 | Manager | As a manager, I want to see a chronological timeline of all actions taken on a loan application so that I understand the full decision history before acting. | Must | Low | US-40 | 8 | Medium | - Manager can view a complete timeline of all actions taken on an application - Timeline shows each action, who performed it, and when - Timeline is shown in chronological order - Timeline cannot be edited or deleted by any user
45 | US-45 | Manager | As a manager, I want to see my branch's key portfolio metrics on a single dashboard so that I can monitor overall health at a glance every day. | Must | High | US-55 | 8 | High | - Manager can view key portfolio metrics for their branch on one dashboard - Dashboard shows metrics such as total disbursed amount, active loans, and NPA ratio - Dashboard reflects the manager's own branch by default - Manager can tap any metric to view the related detailed list
46 | US-46 | Manager | As a manager, I want to filter the portfolio dashboard by officer, branch, or loan product so that I can isolate performance on different basis. | Should | Medium | US-46 | 3 | Medium | - Manager can filter the portfolio dashboard by officer, branch, or loan product - Manager can apply more than one filter at the same time - Dashboard updates instantly when a filter is applied - Manager can clear all filters in a single action
47 | US-47 | Manager | As a manager, I want to see collection efficiency trend across the past months so that I can spot deteriorating repayment patterns before they become NPAs. | Could | Medium | US-46 | 5 | Low | - Manager can view the collection efficiency trend over the past several months - Trend respects any filters currently applied on the dashboard - A noticeable decline in collection efficiency is clearly highlighted - Manager can use this trend to identify accounts at risk of becoming NPAs
48 | US-48 | Manager | As a manager, I want to see all my approved loans that have not yet been disbursed so that I can process them in order. | Must | Low | US-41 | 5 | High | - Manager can view all approved loans that have not yet been disbursed - List shows the approved amount and how long the loan has been waiting - Oldest approved loans are shown first - Tapping an entry takes the manager directly into the disbursement flow
49 | US-49 | Manager | As a manager, I want to verify the borrower's bank account number and IFSC before disbursing so that the loan reaches the correct account. | Must | High | US-49 | 5 | High | - Manager can view the borrower's bank account number and IFSC code before disbursing - System validates the IFSC code before allowing disbursement to proceed - Manager cannot proceed with disbursement if the bank details are invalid or unverified - System clearly shows an error if the verification fails
50 | US-50 | Manager | As a manager, I want to see the full generated EMI schedule for a disbursed loan so that I can verify the amortisation is correct before the borrower's first payment. | Must | Medium | US-50 | 8 | High | - Manager can view the complete EMI schedule generated for a disbursed loan - Schedule shows every instalment with due date and amount - Manager can verify the schedule before the borrower's first payment is due - Schedule is shown as read-only and cannot be edited from this screen
51 | US-51 | Manager | As a manager, I want to see all overdue loans tiered by severity so that I can prioritise the most critical accounts first. | Must | High | US-39 | 5 | High | - Manager can view all overdue loans grouped by severity - Overdue loans are tiered based on how many days they have been overdue - Most critical accounts are clearly highlighted at the top - Manager can sort the list by days overdue or by outstanding amount
52 | US-52 | Manager | As a manager, I want to review the full overdue loan detail and all prior contact history so that I can choose the right resolution path with full context. | Should | High | US-52 | 5 | Medium | - Manager can view the full details of an overdue loan in one place - Manager can view all prior contact history logged for that loan - Manager can log a new contact attempt directly from this screen - Contact history remains visible regardless of what resolution is chosen later
53 | US-53 | Manager | As a manager, I want to restructure an NPA loan so that the borrower can resume repayment on achievable terms in case of any grievance. | Should | High | US-53 | 8 | Medium | - Manager can restructure an NPA loan by setting a revised tenure and/or interest rate - Manager can choose to waive part or all of the pending penalty - System regenerates the EMI schedule based on the new terms - Loan status updates to Restructured once confirmed
54 | US-54 | Manager | As a manager, I want to write off an NPA loan with a mandatory reason so that it is removed from the active portfolio and permanently recorded for audit and regulatory purposes. | Should | High | US-53 | 5 | Medium | - Manager can write off an NPA loan - System requires a reason before the write-off can be confirmed - Written-off loan is removed from the active portfolio - Action is recorded permanently and cannot be reversed from the app
55 | US-55 | Manager | As a manager, I want to escalate an NPA loan to admin with a reason so that cases requiring legal action or regulatory handling can be properly routed. | Should | Medium | US-53 | 3 | Medium | - Manager can escalate an NPA loan to the admin - System requires a reason before the escalation can be submitted - Admin is notified immediately when a loan is escalated - Escalated loan is clearly marked as awaiting admin action
56 | US-56 | Manager | As a manager, I want to generate a portfolio, repayment trend, or NPA report for a selected date range and filter so that I can review branch performance data before sharing it. | Should | High | US-46 | 8 | Medium | - Manager can generate a portfolio, repayment trend, or NPA report - Manager can select a specific date range and apply filters before generating - Report preview matches exactly what was selected - Manager sees a loading indicator while the report is being generated
57 | US-57 | Manager | As a manager, I want to export a generated report so that I can share it with stakeholders. | Should | Low | US-57 | 3 | Medium | - Manager can export a generated report as a PDF or CSV file - Exported file matches exactly what was shown in the report preview - Manager can share the exported file outside the app - System shows an error if the export fails
58 | US-58 | Manager | As a manager, I want to update the interest rate and processing fee and other parameters for a loan product so that our pricing reflects current branch policy. | Could | High | US-65 | 5 | Low | - Manager can update the interest rate, processing fee, and other parameters for a loan product - System only allows changes within the limits set by the admin - Updated parameters apply only to new applications, not existing loans - All changes are recorded for audit purposes
59 | US-59 | Manager | As a manager, I want to send an in-app message to a loan officer regarding their application so that I can request clarification or communicate a decision detail directly. | Should | Low | US-36 | 5 | Low | - Manager can send a message to a loan officer about a specific application - Officer is notified when a new message is received - Message is linked to the relevant loan application - Manager can view the full message history with the officer
60 | US-60 | Admin | As an admin, I want to log in to the app so that I can access administrative functions. | Must | Medium | - | 3 | Highest | - Admin can log in using their employee credentials - System grants access only to the features and data permitted for the admin role - System shows an error for incorrect login credentials - Admin is logged out automatically after a defined period of inactivity
61 | US-61 | Admin | As an admin, I want to reset my password so that I can regain access to the system. | Should | Low | US-61 | 2 | Low | - Admin can request a password reset from the login screen - System sends an OTP to the registered contact for verification - Admin can set a new password that meets the minimum security requirements - All other active sessions are logged out after a successful reset
62 | US-62 | Admin | As an admin, I want to view a loan activity dashboard so that I can monitor system-wide activity. | Must | High | US-46 | 8 | High | - Admin can view a real-time dashboard of loan activity across all branches - Dashboard shows counts of total, pending, approved, rejected, and disbursed applications - Dashboard updates automatically without manual refresh - Admin can tap any count to view the related filtered list
63 | US-63 | Admin | As an admin, I want to manage staff accounts and permissions so that employee access to the system is properly controlled. | Must | High | US-61 | 8 | Highest | - Admin can view a list of all staff accounts - Admin can create a new staff account with name, role, and branch - Admin can edit an existing staff member's details - Admin can activate or deactivate a staff account - Deactivating an account immediately revokes that user's access
64 | US-64 | Admin | As an admin, I want to assign or change staff roles so that permissions match job responsibilities. | Must | Medium | US-64 | 5 | Highest | - Admin can assign or change the role on any staff account - Role change takes effect immediately for that staff member - Staff member's permissions update without needing to log out and back in - Role changes are recorded for audit purposes
65 | US-65 | Admin | As an admin, I want to view a borrower's complete profile so that I can access all customer information. | Must | Medium | US-01 | 5 | High | - Admin can search for and view any borrower's complete profile - Profile includes KYC status, credit history, and full loan history - Admin can search by name, phone number, or borrower ID - Profile is shown as read-only from this screen
66 | US-66 | Admin | As an admin, I want to create and update a loan product so that new products can be offered. | Must | High | US-61 | 8 | Highest | - Admin can create a new loan product with type, interest rate, fees, and tenure/amount limits - Admin can update the details of an existing loan product - New or updated products are available to borrowers immediately once activated - Changes do not affect loans that are already disbursed
67 | US-67 | Admin | As an admin, I want to define and edit loan eligibility criteria so that only qualified borrowers can apply. | Must | Medium | US-67 | 5 | Highest | - Admin can define eligibility criteria for a loan product - Criteria can include minimum income, credit score, age, and employment tenure - System rejects invalid criteria, such as a minimum higher than the maximum - Updated criteria apply only to new applications going forward
68 | US-68 | Admin | As an admin, I want to create and edit notification templates so that system communications remain consistent. | Could | Low | - | 5 | Lowest | - Admin can create and edit notification templates for system events - Templates can include placeholders such as borrower name, amount, and due date - Saved templates apply to all future notifications of that event immediately - System prevents saving a template with broken or invalid placeholders
69 | US-69 | Admin | As an admin, I want to view the audit trail so that I can track system activity. | Must | High | - | 8 | High | - Admin can view a complete audit trail of actions performed across all roles - Each entry shows the actor, the action taken, and when it occurred - Audit trail is read-only and cannot be edited or deleted - Audit trail loads smoothly even with a large volume of records
70 | US-70 | Admin | As an admin, I want to configure and update the required document checklist for each loan type so that borrowers and officers always know exactly which documents must be submitted for a specific loan product. | Must | Medium | US-66 | 5 | Medium | - Admin can define the required document checklist for each loan type - Admin can mark each document as mandatory or optional - Checklist changes apply immediately to new loan applications - Borrowers and officers always see the most current checklist for a loan type

## Legend
COLUMN | VALUES | MEANING
MoSCoW | Must | Core feature — ship without it = broken product
| Should | Important — significantly reduces value if absent
| Could | Nice to have — include only if capacity allows
| Won't | Explicitly out of scope for this release
Risk | Low | Simple CRUD / standard Supabase query — < 1 day
| Medium | Moderate complexity — auth, RLS, joins, Edge Fn — 1-3 days
| High | Complex — payment gateways, PDF gen, real-time, NPA cron, biometric — 3+ days
Points | 2 | Trivial — read-only screen, status display
| 3 | Simple — one DB write, standard UI
| 5 | Moderate — multiple DB tables, some Edge Function logic
| 8 | Complex — multi-step flow, Edge Function chain, external API
| 13 | Very complex — full feature with many edge cases (KYC, loan application)